## project
Project Planner Sprint 2
[6 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Create Database features for account and course playlist | 1 | 2 | 1 | 2 | 100%
CRUD Service for account in Handler | 3 | 3 | 3 | 3 | 100%
CRUD Service for course subscribe in Handler | 3 | 3 |  |  | 0%
Prototype for Mobile App | 1 | 8 | 1 | 5 | 100%
Add to Client create account/login feature | 7 | 3 | 6 |  | 20%
Add to Client two steps verification with google authenticator | 7 | 3 |  |  | 0%
Add to Client Account management page | 10 | 3 |  |  | 0%
Add to Client link beside course info to subscribe the course | 10 | 2 |  |  | 0%
Add to Client browse playlist link on browse submenu if user has logged in | 12 | 2 |  |  | 0%
Add to Client drop down menu with playlist | 12 | 2 |  |  | 0%
Add to Client course info page link to choose course, login popup if not logged in | 7 | 2 |  |  | 0%